## 1. Cover Page
RELEASE PLAN V 1.1
| Start Date | 2022-10-03
| Organizations | Retro Team
| Product Owner | Truong Bao Khoi
| Scrum Master | Nguyen Tan Duy
| Mentor | Bui Minh Phung
Revision History
| Version | Date | Author | Content
| 1.0 | 2022-10-09 | Huynh Phuc Thien | Creates template
| 1.1 | 2022-10-09 | Huynh Phuc Thien | Update release plan
| 1.1 | 2022-10-10 | Nguyen Tan Duy | Update release date according to mentor's suggestion
| 1.1 | 2022-10-12 | Tran Hung Dung | Review document

## 2. Release Plan
Release Plan
AT RISK | RELEASE # | SPRINT | FEATURE NAME | CATEGORY | START | END | DURATION (DAY) | EFFORT | STATUS | RELEASE DATE | GOAL
| 1 | 1 | Login/Logout with Faculty board's VLU mail | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned | 2022-12-24 | Faculty board can login/logout with Faculty board's VLU mail that has been authorized as Faculty board role
|  | 1 | View list of users | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can see list of all user accounts registered into the system | Planned
|  | 1 | Create user | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can create a new user | Ongoing
|  | 1 | Update user | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can update and authorize user's account | Released
|  | 1 | Delete user | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can delete user's account
|  | 1 | Search user | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can search user's account
|  | 1 | View list of terms | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can view list of terms
|  | 1 | Create term | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can create a new term
|  | 1 | Update term | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can update a term
|  | 1 | Delete term | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can delete a term
|  | 1 | Search term | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can search terms
|  | 1 | View list of majors | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can view list of majors
|  | 1 | Create major | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can create a new major
|  | 1 | Update major | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can update a major
|  | 1 | Delete major | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can delete a major
|  | 1 | Search major | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Faculty board can search majors
|  | 1 | Update User Profile | Function | 24/10/2022 | 2022-12-11 | 18 | 3 | Planned |  | Faculty board can update their own user profile
|  | 1 | Login/Logout with Department head's | Function | 24/10/2022 | 2022-12-11 | 18 | 2 | Planned |  | Department head can login/logout with Department head's VLU mail that has been authorized as Department head role
|  | 1 | Update User Profile | Function | 24/10/2022 | 2022-12-11 | 18 | 3 | Planned |  | Department head can update their own user profile
|  | 1 | Login/Logout with Lecturer's VLU mail | Function | 24/10/2022 | 2022-12-11 | 18 | 3 | Planned |  | Lecturer can login/logout with Lecturer's VLU mail that has been authorized as Lecturer role
|  | 1 | Update User Profile | Function | 24/10/2022 | 2022-12-11 | 18 | 3 | Planned |  | Lecturer can update their own user profile
|  | 2 | Import timetable | Function | 14/11/2022 | 2022-03-12 | 18 | 8 | Planned |  | Faculty board can import timetable into the system
|  | 2 | Assign lecturer | Function | 14/11/2022 | 2022-03-12 | 18 | 20 | Planned |  | Faculty board can use timetable to assign lecturer
|  | 2 | Delete class | Function | 14/11/2022 | 2022-03-12 | 18 | 3 | Planned |  | Faculty board can delete a class on timetable
|  | 2 | View personal timetable | Function | 14/11/2022 | 2022-03-12 | 18 | 5 | Planned |  | Faculty board can view their own personal timetable
|  | 2 | View faculty timetable | Function | 14/11/2022 | 2022-03-12 | 18 | 8 | Planned |  | Faculty board can view whole faculty timetable based on week
|  | 3 | Export timetable | Function | 2022-05-12 | 24/12/2022 | 18 | 8 | Planned |  | Faculty board can export timetable
|  | 3 | Assign lecturer | Function | 2022-05-12 | 24/12/2022 | 18 | 8 | Planned |  | Department head can use timetable to assign lecturer
|  | 3 | Delete class | Function | 2022-05-12 | 24/12/2022 | 18 | 3 | Planned |  | Department head can delete a class on timetable
|  | 3 | View personal timetable | Function | 2022-05-12 | 24/12/2022 | 18 | 5 | Planned |  | Department head can view their own personal timetable
|  | 3 | View faculty timetable | Function | 2022-05-12 | 24/12/2022 | 18 | 5 | Planned |  | Department head can view whole faculty timetable based on week
|  | 3 | View personal timetable | Function | 2022-05-12 | 24/12/2022 | 18 | 2 | Planned |  | Lecturer can view their own personal timetable
|  | 3 | View faculty timetable | Function | 2022-05-12 | 24/12/2022 | 18 | 5 | Planned |  | Lecturer can view whole faculty timetable based on week
| 2 | 4 | View list of curriculums | Function | 26/12/2022 | 14/01/2023 | 18 | 2 | Planned | 2023-04-01 | Faculty board can view list of curriculums
|  | 4 | Search curriculums | Function | 26/12/2022 | 14/01/2023 | 18 | 2 | Planned |  | Faculty board can search curriculums
|  | 4 | View hours in term | Function | 26/12/2022 | 14/01/2023 | 18 | 8 | Planned |  | Faculty board can view statistics about the number of hours that each lecturer has to teach each term
|  | 4 | View hours in year | Function | 26/12/2022 | 14/01/2023 | 18 | 8 | Planned |  | Faculty board can view statistics about the number of hours that each lecturer has to teach each year
|  | 4 | View classes in week | Function | 26/12/2022 | 14/01/2023 | 18 | 5 | Planned |  | Faculty board can view statistics about the number of classes that each lecturer has to teach each week
|  | 4 | View curriculums in term | Function | 26/12/2022 | 14/01/2023 | 18 | 8 | Planned |  | Faculty board can view statistics about the number of curriculums that each lecturer has to teach each term
|  | 4 | View lecturer timetable | Function | 26/12/2022 | 14/01/2023 | 18 | 8 | Planned |  | Faculty board can view multiple lecturers timetable based on week
|  | 5 | View hours in term | Function | 30/01/2023 | 18/02/2023 | 18 | 5 | Planned |  | Department head can view statistics about the number of hours that each lecturer has to teach each term
|  | 5 | View hours in year | Function | 30/01/2023 | 18/02/2023 | 18 | 5 | Planned |  | Department head can view statistics about the number of hours that each lecturer has to teach each year
|  | 5 | View classes in week | Function | 30/01/2023 | 18/02/2023 | 18 | 5 | Planned |  | Department head can view statistics about the number of classes that each lecturer has to teach each week
|  | 5 | View curriculums in term | Function | 30/01/2023 | 18/02/2023 | 18 | 5 | Planned |  | Department head can view statistics about the number of curriculums that each lecturer has to teach each term
|  | 5 | View lecturer timetable | Function | 30/01/2023 | 18/02/2023 | 18 | 5 | Planned |  | Department head can view multiple lecturers timetable based on week
|  | 6 | View personal hours in term | Function | 2023-02-20 | 2023-03-11 | 18 | 5 | Planned |  | Lecturer can view statistics about the number of hours that each lecturer has to teach each term
|  | 6 | View personal hours in year | Function | 2023-02-20 | 2023-03-11 | 18 | 5 | Planned |  | Lecturer can view statistics about the number of hours that each lecturer has to teach each year
|  | 6 | View personal classes in week | Function | 2023-02-20 | 2023-03-11 | 18 | 5 | Planned |  | Lecturer can view statistics about the number of classes that each lecturer has to teach each week
|  | 6 | View personal curriculums in term | Function | 2023-02-20 | 2023-03-11 | 18 | 5 | Planned |  | Lecturer can view statistics about the number of curriculums that each lecturer has to teach each term
|  | 6 | View lecturer timetable | Function | 2023-02-20 | 2023-03-11 | 18 | 5 | Planned |  | Lecturer can view multiple lecturers timetable based on week